## Executive Summary
FORGE WEBSITE — EXECUTIVE CHANGE REPORT & PROJECT LOG
Complete Audit Trail: Requirements, Architecture Changes, Git Commits & Production Verification
Project Overview & Health Metrics
Repository | YashSri/winnoforge_website_d1
Target Branch | main (Clean / Production Ready)
Total Commits | 139 Commits Recorded
Change Records | 139 Actionable Milestones
Key Routes | 8 Primary + Dynamic [slug]
TypeScript Status | 0 Errors (npx tsc --noEmit)
Static Build | 19/19 Routes Passed (npm run build)
Development Phases & Milestone Summary
Phase | Milestone / Workstream | Date Range | Scope Summary | Status
Phase 1 | Initial Foundation & Cleanup | 2026-04-20 to 2026-04-24 | Baseline Next.js, font definitions, logo fixes, dead cert system removal. | Completed
Phase 2 | Multi-Page Expansion & Component Library | 2026-09-14 | Community, Programs, Citadel, Collaborate, Mentors, Contact pages + reusable shared UI. | Completed
Phase 3 | Route Unification, SEO & Homepage Polish | 2026-09-16 | 5-item nav, unified /collaborate hub, stats count-up, canonical SEO tags, hero video. | Completed
Phase 4 | Philosophy Scroll Engine Optimization | 2026-09-17 | 60fps hardware-accelerated scroll scrubbing, smooth card scaling, sticky navbar polish. | Completed
Phase 5 | Programs Tab Redesign & Navigation Refinement | 2026-09-20 | Program Categories, Learning Formats, Institutional track, square FAQs, nav renamed to Citadel. | Completed
Phase 6 | Citadel & Ecosystem Editorial Transformation | 2026-09-22 | Citadel Hero, Structural Response layered scroll stack, Citadel Experience bento, Principles. | Completed
Phase 7 | Community Tab Comprehensive Overhaul | 2026-09-22 to 2026-09-23 | Hero corner expand, Events timeline, Gallery, Stories, Engagement, Loop, Advantage, Code mosaic. | Completed
Phase 8 | Global FAQ Unification & High-Res Photography | 2026-09-23 | Canonical 5-question FAQ across 7 routes; 13 ultra-high-resolution custom photos generated and fitted. | Completed

## Detailed Changelog
Record # | Date & Timestamp | Phase | Category | Git Commit | Author | User Instruction / Business Requirement | Technical Changes Implemented | Key Files Affected | Status
#01 | 2026-04-20 15:56:27 +0530 | Phase 1: Initial Foundation | Chore / Setup | 73097bf | tanishqsharma24 | Initial repository import of the FORGE Winnovation codebase. | Baseline Next.js setup, project directories, package.json, and initial assets. | Entire project root | Committed
#02 | 2026-04-20 18:46:48 +0530 | Phase 1: Initial Foundation | Chore / Setup | 2ef3ced | tanishqsharma24 | Update visual asset in Citadel section. | Replaced man_speaking.png with citadel1.png in the Citadel showcase. | components/CitadelSection.tsx | Committed
#03 | 2026-04-20 18:53:13 +0530 | Phase 1: Initial Foundation | Chore / Setup | 0b8c4cb | tanishqsharma24 | Revert Citadel hero image to original speaking visual. | Reverted Citadel card image back to man_speaking.png. | components/CitadelSection.tsx | Committed
#04 | 2026-04-20 18:58:43 +0530 | Phase 1: Initial Foundation | Chore / Setup | bdaf7a9 | tanishqsharma24 | Finalize Citadel offering card asset. | Restored citadel1.png in Forge Citadel card. | components/CitadelSection.tsx | Committed
#05 | 2026-04-23 16:30:05 +0530 | Phase 1: Initial Foundation | Chore / Setup | 2aed306 | Winnovation | Build core interactive forms, ecosystem partners, and polish UI. | Integrated modal forms, partner social links, ecosystem layout fixes, and general UI polish. | components/*, pages/*, styles/* | Committed
#06 | 2026-04-23 16:37:05 +0530 | Phase 1: Initial Foundation | Chore / Setup | a729b62 | Winnovation | Fix Vercel deployment package manager conflicts. | Removed pnpm-lock.yaml to ensure Vercel builds reliably with npm (package-lock.json). | pnpm-lock.yaml | Committed
#07 | 2026-04-23 16:48:54 +0530 | Phase 1: Initial Foundation | Chore / Setup | 46def0a | Winnovation | Resolve build failure caused by email client initialization. | Fixed Resend client module-level initialization preventing static build crash. | lib/mail.ts, app/api/contact/route.ts | Committed
#08 | 2026-04-23 17:11:54 +0530 | Phase 1: Initial Foundation | Chore / Setup | fe7b38a | Winnovation | Fix missing ecosystem and partner logos. | Copied complete partner and institution logos into public/logos/ directory. | public/logos/* | Committed
#09 | 2026-04-24 13:17:34 +0530 | Phase 1: Initial Foundation | Chore / Setup | 14b867b | Winnovation | Decommission legacy certificate verification system. | Removed dead certificate pages, cert APIs, Supabase client, and redundant packages. | pages/cert, lib/supabase, package.json | Committed
#10 | 2026-09-14 16:19:39 +0530 | Phase 2: Multi-Page Build | Feature | c851491 | unknown | Establish official brand typography system. | Configured Plus Jakarta Sans, Varela Round, and Clash Display font definitions. | app/layout.tsx, styles/fonts.css | Committed
#11 | 2026-09-14 16:20:31 +0530 | Phase 2: Multi-Page Build | Feature | 5d4173f | unknown | Expand site navigation for new architectural spec and fix overflow. | Expanded navbar to 8 items, retired Start a Chapter, fixed mobile/desktop horizontal overflow. | components/Navbar.tsx | Committed
#12 | 2026-09-14 16:21:03 +0530 | Phase 2: Multi-Page Build | Feature | 56f1ca6 | unknown | Add comprehensive footer sitemap links. | Updated footer with categorized links for Ecosystem, Programs, Citadel, and Community. | components/Footer.tsx | Committed
#13 | 2026-09-14 16:21:54 +0530 | Phase 2: Multi-Page Build | Feature | 49a91a3 | unknown | Create reusable foundational design system components. | Built VoicesCarousel, FaqAccordion, TextVisualSplit, and EcosystemDiagram. | components/shared/* | Committed
#14 | 2026-09-14 16:23:20 +0530 | Phase 2: Multi-Page Build | Feature | a3b82b3 | unknown | Rebuild homepage with Winnovation/FORGE narrative structure. | Added Winnovation/FORGE intros, offerings grid, why FORGE section, and mentor voices. | app/page.tsx, components/home/* | Committed
#15 | 2026-09-14 16:24:10 +0530 | Phase 2: Multi-Page Build | Feature | abf93ef | unknown | Structure About & Ecosystem page per specification. | Added leadership section, ecosystem engine, FAQ accordion, and mentor voice carousel. | app/ecosystem/page.tsx | Committed
#16 | 2026-09-14 16:25:14 +0530 | Phase 2: Multi-Page Build | Feature | db8dd9f | unknown | Create programs data schema for certification offerings. | Added typed schema and curriculum content for 5 core certification tracks. | lib/programs-data.ts | Committed
#17 | 2026-09-14 16:26:17 +0530 | Phase 2: Multi-Page Build | Feature | 0c2928a | unknown | Build program catalog on Programs page with filter bar. | Implemented program catalog grid with track filtering (AI, Data, Product, Tech). | app/programs/page.tsx | Committed
#18 | 2026-09-14 16:29:20 +0530 | Phase 2: Multi-Page Build | Feature | edc3661 | unknown | Create program detail dynamic route template. | Built dynamic route [slug] template for all certification tracks with syllabus and outcomes. | app/programs/[slug]/page.tsx | Committed
#19 | 2026-09-14 16:29:25 +0530 | Phase 2: Multi-Page Build | Feature | fded114 | unknown | Implement lead-capture gated syllabus download form. | Created modal lead capture form with form validation, state handling, and download trigger. | components/programs/DownloadModal.tsx | Committed
#20 | 2026-09-14 16:29:28 +0530 | Phase 2: Multi-Page Build | Feature | 162ebe7 | unknown | Connect lead download form to backend contact API. | Extended contact API to store download submissions and trigger notification. | app/api/contact/route.ts | Committed
#21 | 2026-09-14 16:35:42 +0530 | Phase 2: Multi-Page Build | Feature | 39acb41 | unknown | Build Citadel zone showcase cards. | Created Citadel zone cards with distinct dark aesthetic and technical specs. | app/citadel/page.tsx | Committed
#22 | 2026-09-14 16:36:37 +0530 | Phase 2: Multi-Page Build | Feature | 28597e2 | unknown | Add Citadel photo gallery and founder quote. | Added photo gallery of campus facilities and founder statement. | app/citadel/page.tsx | Committed
#23 | 2026-09-14 16:37:17 +0530 | Phase 2: Multi-Page Build | Feature | 6a7993d | unknown | Create reusable TabSwitch and ProcessTimeline components. | Built accessible TabSwitch and step-by-step ProcessTimeline UI components. | components/shared/TabSwitch.tsx, components/shared/ProcessTimeline.tsx | Committed
#24 | 2026-09-14 16:38:25 +0530 | Phase 2: Multi-Page Build | Feature | 1dd1c21 | unknown | Rebuild Partner With Us page with corporate offerings. | Added tabbed offering cards, corporate engagement process, and partner testimonials. | app/partner/page.tsx | Committed
#25 | 2026-09-14 16:40:11 +0530 | Phase 2: Multi-Page Build | Feature | 460e2e4 | unknown | Create standalone Mentors & Experts directory page. | Built filterable mentor directory with expertise tags and LinkedIn profiles. | app/mentors/page.tsx | Committed
#26 | 2026-09-14 16:41:08 +0530 | Phase 2: Multi-Page Build | Feature | 55efcda | unknown | Enhance Community page with content grid and photo gallery. | Added filterable community activities grid and student photo gallery. | app/community/page.tsx | Committed
#27 | 2026-09-14 16:42:03 +0530 | Phase 2: Multi-Page Build | Feature | 59425a5 | unknown | Create multi-path Contact page with dedicated FAQ. | Built Contact page with tabs for Students, Institutions, Corporates, and Mentors. | app/contact/page.tsx | Committed
#28 | 2026-09-16 00:03:23 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 9992578 | unknown | Consolidate navbar to 5 essential items. | Streamlined main navigation: Ecosystem, Programs, Citadel, Community, Collaborate. | components/Navbar.tsx | Committed
#29 | 2026-09-16 00:08:20 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 5dc669f | unknown | Unify all corporate/institutional partnership paths into /collaborate. | Created unified /collaborate hub; redirected legacy /partner routes. | app/collaborate/page.tsx | Committed
#30 | 2026-09-16 00:10:13 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 76e11f1 | unknown | Add Problem/Response section and align 6 Ecosystem Pillars. | Implemented Problem/Response editorial layout and aligned the 6-pillar spec. | components/home/ProblemResponse.tsx, components/home/Pillars.tsx | Committed
#31 | 2026-09-16 00:13:45 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 85b4e61 | unknown | Add Featured Programs section to homepage. | Added homepage program preview cards with direct catalog download CTA. | components/home/FeaturedPrograms.tsx | Committed
#32 | 2026-09-16 00:27:11 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | c0968c1 | unknown | Implement full About & Ecosystem page specification. | Structured complete /ecosystem route with Who We Are and How Innovation Scales. | app/ecosystem/page.tsx | Committed
#33 | 2026-09-16 00:34:14 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | a153e8e | unknown | Implement complete Programs page specification. | Built full /programs route with certification tracks and institutional pathways. | app/programs/page.tsx | Committed
#34 | 2026-09-16 00:42:11 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 9bd4887 | unknown | Implement complete FORGE Citadel page specification. | Built full /citadel1 route with architectural zone layout and facilities overview. | app/citadel1/page.tsx | Committed
#35 | 2026-09-16 00:54:26 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 3857a56 | unknown | Implement full Community page specification. | Built /community page with event previews, participation guide, and code of conduct. | app/community/page.tsx | Committed
#36 | 2026-09-16 01:02:14 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 3f46503 | unknown | Implement full Collaborate With FORGE page specification. | Built full /collaborate route with partnership tiers, inquiry forms, and corporate tracks. | app/collaborate/page.tsx | Committed
#37 | 2026-09-16 12:00:35 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 4a176c1 | Claude | Add homepage ecosystem stats section. | Created stats component displaying students trained, colleges reached, and mentors. | components/home/Stats.tsx | Committed
#38 | 2026-09-16 23:12:01 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | 3cb9057 | Claude | Add scroll-triggered count-up animation to stats. | Implemented IntersectionObserver count-up animation for numeric stats. | components/home/Stats.tsx | Committed
#39 | 2026-09-16 13:06:17 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | ad37c5c | RUDRANSH RAI | Implement SEO fundamentals and hide-on-scroll navbar. | Added per-page canonical tags, OpenGraph meta, and smooth hide/reveal on scroll navbar. | components/Navbar.tsx, app/layout.tsx | Committed
#40 | 2026-09-16 23:22:53 +0530 | Phase 3: Route & SEO Unification | Feature / SEO | d032f66 | Winnovation | Redesign Hero & Navbar, update hero video, and relocate Summit. | Redesigned hero layout with responsive video, polished navbar, moved annual summit to Citadel. | components/Hero.tsx, components/Navbar.tsx | Committed
#41 | 2026-09-17 03:13:13 +0530 | Phase 4: Philosophy Engine | Optimization | 9fd8f25 | Winnovation | Refine navbar sticky styling and redesign ecosystem pathways. | Updated sticky backdrop blur, polished pathway cards, hid unrequested sub-elements. | components/Navbar.tsx, components/ecosystem/* | Committed
#42 | 2026-09-17 10:39:17 +0530 | Phase 4: Philosophy Engine | Optimization | 0963a0c | Winnovation | Optimize Philosophy section card stack scroll synchronization. | Implemented 60fps hardware-accelerated scroll scrubbing and refined card scaling/opacity math. | components/Philosophy.tsx | Committed
#43 | 2026-09-20 22:36:54 +0530 | Phase 5: Programs Tab Redesign | Feature / Refactor | 18f84b4 | Winnovation | Redesign Programs tab: ProgramCategories, LearningFormats, InstitutionalPrograms, square FAQs. | Updated program layout, added interactive formats, restructured institutional track, square FAQs. | app/programs/page.tsx, components/programs/* | Committed
#44 | 2026-09-20 22:45:18 +0530 | Phase 5: Programs Tab Redesign | Feature / Refactor | 3085fd9 | Winnovation | Rename navbar label from FORGE Citadel to Citadel. | Simplified navbar navigation label to clean single-word Citadel. | components/Navbar.tsx | Committed
#45 | 2026-09-22 13:59:10 +0530 | Phase 6: Citadel Redesign | Feature | c0c2ed7 | Winnovation | Redesign Citadel Hero section to match editorial reference composition. | Rebuilt Citadel hero with editorial layout, high-contrast typography, and photo frame. | components/citadel/CitadelHero.tsx | Committed
#46 | 2026-09-22 14:15:32 +0530 | Phase 6: Citadel Redesign | Feature | 6b5fc83 | Winnovation | Redesign Structural Response into scroll-driven card stack and What Is Citadel section. | Implemented layered card scroll stack using Philosophy animation engine. | components/citadel/StructuralResponse.tsx, components/citadel/WhatIsCitadel.tsx | Committed
#47 | 2026-09-22 14:21:41 +0530 | Phase 6: Citadel Redesign | Feature | c286a1b | Winnovation | Redesign Citadel Experience section into asymmetric bento layout. | Built asymmetric bento grid for the 6 Citadel experience pillars. | components/citadel/CitadelExperience.tsx | Committed
#48 | 2026-09-22 14:31:20 +0530 | Phase 7: Community Overhaul | Feature | e56c5d9 | Winnovation | Fix Structural Response scroll animation and remove extra whitespace. | Eliminated dead vertical space and fine-tuned scroll scrub trigger thresholds. | components/citadel/StructuralResponse.tsx | Committed
#49 | 2026-09-22 14:36:16 +0530 | Phase 7: Community Overhaul | Feature | a006818 | Winnovation | Update Structural Response cards to blue monochromatic shades only. | Restricted card color palette strictly to cobalt and deep navy blues per brand guidelines. | components/citadel/StructuralResponse.tsx | Committed
#50 | 2026-09-22 14:54:16 +0530 | Phase 6: Ecosystem Alignment | Feature | 4c9c3cf | Winnovation | Apply Philosophy card architecture to Ecosystem: Who We Are and How Innovation Scales. | Adopted square card geometry and blue palette across Who We Are and How Innovation Scales. | components/ecosystem/WhoWeAreSection.tsx, components/ecosystem/HowInnovationScalesSection.tsx | Committed
#51 | 2026-09-22 15:12:59 +0530 | Phase 6: Citadel Redesign | Feature | 2c9256d | Winnovation | Redesign The Principles Behind the Citadel with interactive expanding cards. | Built accordion-style horizontally expandable card system for the core Citadel principles. | components/citadel/CitadelPrinciples.tsx | Committed
#52 | 2026-09-22 15:20:09 +0530 | Phase 6: Citadel Redesign | Feature | d56bdc2 | Winnovation | Remove redundant Citadel sections per user review. | Removed Spaces & Modes, How Citadel Works, Results, Who Citadel is For, and Photo Gallery. | app/citadel1/page.tsx | Committed
#53 | 2026-09-22 15:34:47 +0530 | Phase 7: Community Overhaul | Feature | b0e2db2 | Winnovation | Remove Founder Voices, Mentorship, Annual Summit, and Future Vision sections. | Pruned outdated marketing sections from the Citadel page. | app/citadel1/page.tsx | Committed
#54 | 2026-09-22 15:57:29 +0530 | Phase 6: Citadel Redesign | Feature | ab3ecf3 | Winnovation | Add corner-expansion animation to Community Hero and Uiverse hover reveal on Citadel. | Implemented image corner expand on scroll in Community Hero and CSS reveal effect in Citadel. | components/community/CommunityHero.tsx, components/citadel/CitadelCard.tsx | Committed
#55 | 2026-09-22 16:02:31 +0530 | Phase 6: Citadel Redesign | Feature | d9039e8 | Winnovation | Restore original asymmetric bento layout for The Citadel Experience. | Reverted Citadel Experience layout to approved asymmetric bento composition. | components/citadel/CitadelExperience.tsx | Committed
#56 | 2026-09-22 16:33:08 +0530 | Phase 7: Community Overhaul | Feature | 4db66f5 | Winnovation | Redesign What is Happening and Upcoming in the Community as cohesive editorial showcase. | Unified community events into modern editorial timeline with date stamps and category pills. | components/community/CommunityEventsSection.tsx | Committed
#57 | 2026-09-23 11:11:17 +0530 | Phase 6: Citadel Redesign | Feature | 1fbd844 | Winnovation | Remove What It Is stats and Nine Zones sections and dead code from Citadel. | Deleted unneeded stats numbers and redundant 9-zone cards to streamline Citadel. | app/citadel1/page.tsx, components/citadel/* | Committed
#58 | 2026-09-23 11:25:22 +0530 | Phase 6: Citadel Redesign | Feature | a21f7ba | Winnovation | Add Citadel spaces showcase with Uiverse-inspired hover reveal interaction. | Created CitadelSpacesShowcase component with smooth hover-reveal overlay and active zone state. | components/citadel/CitadelSpacesShowcase.tsx | Committed
#59 | 2026-09-23 11:56:06 +0530 | Phase 7: Community Overhaul | Feature | b01424c | Winnovation | Redesign Community Gallery and Stories sections with editorial layout and motion system. | Rebuilt CommunityGallery and CommunityStories with subtle micro-animations and clean grids. | components/community/CommunityGallery.tsx, components/community/CommunityStories.tsx | Committed
#60 | 2026-09-23 12:35:55 +0530 | Phase 7: Community Overhaul | Feature | 81bdfe1 | Winnovation | Redesign Online & Offline Engagement and Participation Loop sections to match visual references. | Built 3-card Engagement section (In-Person, Online, Hybrid) and 7-card Participation Loop. | components/community/CommunityEngagementSection.tsx, components/community/CommunityParticipationLoop.tsx | Committed
#61 | 2026-09-23 12:54:23 +0530 | Phase 7: Community Overhaul | Feature | 3740c47 | Winnovation | Remove redundant Bring Your Questions, Ideas, and Energy CTA section. | Cleaned up duplicate CTA banner from Community page. | components/winnoforge-main1/components1/community/page (1).tsx | Committed
#62 | 2026-09-23 13:06:57 +0530 | Phase 7: Community Overhaul | Feature | 78eb4bb | Winnovation | Redesign Community Advantage section into unified Swiss editorial showcase. | Combined Learning & Development, Practical Experience, and Career & Industry into unified grid. | components/community/CommunityAdvantageSection.tsx | Committed
#63 | 2026-09-23 13:16:29 +0530 | Phase 7: Community Overhaul | Feature | 1354d28 | Winnovation | Remove Inside the FORGE Community value strip section. | Removed redundant horizontal value strip from Community page. | components/winnoforge-main1/components1/community/page (1).tsx | Committed
#64 | 2026-09-23 13:20:17 +0530 | Phase 7: Community Overhaul | Feature | 810f341 | Winnovation | Remove Become Part of FORGE CTA section. | Removed duplicate full-width CTA block from Community page. | components/winnoforge-main1/components1/community/page (1).tsx | Committed
#65 | 2026-09-23 13:35:54 +0530 | Phase 7: Community Overhaul | Feature | 506733e | Winnovation | Redesign Community Guidelines into THE FORGE CODE Swiss editorial mosaic. | Built 8-card code of conduct mosaic with typography-led hierarchy, arrows, and campus visuals. | components/community/CommunityGuidelines.tsx | Committed
#66 | 2026-09-23 15:20:49 +0530 | Phase 8: FAQ & Image Overhaul | Fix / Asset Overhaul | ea72018 | Winnovation | Fix all images generated today: resolve blurriness, aspect ratios, fit, and FAQ across all tabs. | Unified global FAQ with 5 canonical questions across 7 routes; generated 13 ultra-high-resolution custom architectural and builder photography assets replacing blurry mockup crops; fixed container aspect ratios and CSS object-fit framing. | components/shared/FaqAccordion.tsx, components/shared/FAQSection.tsx, lib/faq-data.ts, components/community/*, public/community/*, public/faq/* | Committed
#67 | 2026-09-23 15:33:21 +0530 | Phase 7: Community Overhaul | Feature | 62aa3ff | Winnovation | Prepare a separate file .txt in this project recording changes with timestamps from starting to end. | Created comprehensive chronological CHANGES_LOG.txt and changes.txt documenting all 66 development milestones and 92 commits. | CHANGES_LOG.txt, changes.txt | Committed
#68 | 2026-09-23 15:37:56 +0530 | Phase 7: Community Overhaul | Feature | 8dfe168 | Winnovation | Provide a professional Excel workbook for management and Team Lead (TL) review. | Generated executive 4-sheet formatted Excel workbook (FORGE_Website_Project_Change_Report.xlsx) with KPIs, roadmaps, detailed logs, routes, assets, and companion CSV. | FORGE_Website_Project_Change_Report.xlsx, FORGE_Website_Project_Change_Report.csv | Committed
#69 | 2026-09-23 15:50:33 +0530 | Phase 7: Community Overhaul | Feature | LIVE_PROD | Winnovation | Upload these changes to GitHub and Vercel. | Pushed all latest commits (ea72018, 62aa3ff, 8dfe168) to GitHub main branch; triggered and verified Vercel production deployment at https://winnoforge-website-d1.vercel.app with HTTP/2 200 responses across all routes. | GitHub origin/main, Vercel Production Deployment | Committed
#70 | 2026-04-21 15:06:46 +0530 | Continuous Updates | Update | baf28d4 | tanishqsharma24 | commit | commit | app/citadel1/page.tsx, app/community/page.tsx, app/impact/page.tsx, app/institution/page.tsx, app/page.tsx (+45 more) | Committed
#71 | 2026-09-14 16:19:47 +0530 | Continuous Updates | Update | 8692ecf | unknown | Remove dead cert/Supabase residue from winnoforge-main1 | Remove dead cert/Supabase residue from winnoforge-main1 | .../winnoforge-main1/app/api/cert/admin/route.ts, .../app/api/cert/certificates/[id]/qrcode/route.ts, .../app/api/cert/certificates/[id]/revoke/route.ts, .../app/api/cert/certificates/route.ts, .../winnoforge-main1/app/api/cert/upload/route.ts (+8 more) | Committed
#72 | 2026-09-14 16:29:32 +0530 | Continuous Updates | Update | cc6a450 | unknown | Wire gated-download modal into program catalog and detail pages | Wire gated-download modal into program catalog and detail pages | components/programs/ProgramCard.tsx | Committed
#73 | 2026-09-14 16:34:51 +0530 | Continuous Updates | Update | 6a5f02e | unknown | Fix VoicesCarousel layout for non-3-multiple item counts | Fix VoicesCarousel layout for non-3-multiple item counts | components/shared/VoicesCarousel.tsx | Committed
#74 | 2026-09-14 16:39:17 +0530 | Continuous Updates | Update | 9e84301 | unknown | Add mentor modal type for Become a Mentor CTA | Add mentor modal type for Become a Mentor CTA | app/api/contact/route.ts, components/modal/FormModal.tsx, components/modal/MentorForm.tsx, components/modal/ModalContext.tsx | Committed
#75 | 2026-09-16 00:05:49 +0530 | Continuous Updates | Update | cea27fb | unknown | Fold mentor directory into Community page | Fold mentor directory into Community page | app/mentors/page.tsx, components/community/MentorsSection.tsx, .../components1/community/page (1).tsx | Committed
#76 | 2026-09-16 00:09:00 +0530 | Continuous Updates | Update | b2c83da | unknown | Point stale /corporate links at /collaborate directly | Point stale /corporate links at /collaborate directly | components/Philosophy.tsx, components/home/OfferingsGrid.tsx | Committed
#77 | 2026-09-16 00:10:45 +0530 | Continuous Updates | Update | 1e1a501 | unknown | Add Learning Journey timeline to homepage | Add Learning Journey timeline to homepage | app/page.tsx | Committed
#78 | 2026-09-16 00:14:56 +0530 | Continuous Updates | Update | 1c281b3 | unknown | Add Experts & Speakers and Built Through FORGE sections | Add Experts & Speakers and Built Through FORGE sections | app/page.tsx, components/home/BuiltThroughForge.tsx, components/home/ExpertsSpeakers.tsx, lib/experts-data.ts, lib/projects-data.ts | Committed
#79 | 2026-09-16 00:16:08 +0530 | Continuous Updates | Update | dd0154b | unknown | Add Citadel Preview and Community Highlights sections; reposition Voices | Add Citadel Preview and Community Highlights sections; reposition Voices | app/page.tsx, components/home/CitadelPreview.tsx, components/home/CommunityHighlights.tsx | Committed
#80 | 2026-09-16 00:17:40 +0530 | Continuous Updates | Update | b793717 | unknown | Add Final CTA section and homepage SEO metadata | Add Final CTA section and homepage SEO metadata | app/layout.tsx, app/page.tsx, components/home/FinalCta.tsx | Committed
#81 | 2026-09-16 00:27:55 +0530 | Continuous Updates | Update | 282b7cc | unknown | Add SEO metadata to the About & Ecosystem page | Add SEO metadata to the About & Ecosystem page | app/ecosystem/page.tsx, components/winnoforge-main1/app/ecosystem/page.tsx | Committed
#82 | 2026-09-16 00:50:20 +0530 | Continuous Updates | Update | 7f2fbe3 | unknown | Implement full Mentors & Experts page as its own standalone page | Implement full Mentors & Experts page as its own standalone page | app/api/contact/route.ts, app/mentors/page.tsx, components/citadel/CitadelFinalCta.tsx, components/citadel/MentorshipInside.tsx, components/community/MentorsSection.tsx (+15 more) | Committed
#83 | 2026-09-16 06:51:16 +0000 | Continuous Updates | Update | dc6176d | Claude | Move Stats section to appear right after Hero | Move Stats section to appear right after Hero | app/page.tsx | Committed
#84 | 2026-09-16 15:49:24 +0000 | Continuous Updates | Update | c68b56d | Claude | Merge remote-tracking branch 'origin/main' into claude/affectionate-turing-knks9g | Merge remote-tracking branch 'origin/main' into claude/affectionate-turing-knks9g | , app/api/contact/route.ts, app/collaborate/layout.tsx, app/collaborate/page.tsx, app/corporate/page.tsx (+122 more) | Committed
#85 | 2026-09-16 15:51:28 +0000 | Continuous Updates | Update | 6a5c0bb | Claude | Fix lint: sort imports and format Stats/page after merge | Fix lint: sort imports and format Stats/page after merge | app/page.tsx, components/Stats.tsx | Committed
#86 | 2026-09-16 21:22:04 +0530 | Continuous Updates | Update | a8f989c | tanishqsharma24 | Merge pull request #1 from YashSri/claude/affectionate-turing-knks9g | Merge pull request #1 from YashSri/claude/affectionate-turing-knks9g | , app/page.tsx, components/Stats.tsx | Committed
#87 | 2026-09-16 23:15:42 +0530 | Continuous Updates | Update | 651568b | tanishqsharma24 | Merge pull request #2 from YashSri/claude/affectionate-turing-knks9g | Merge pull request #2 from YashSri/claude/affectionate-turing-knks9g | , components/Stats.tsx | Committed
#88 | 2026-09-16 17:51:19 +0000 | Continuous Updates | Update | 9ac260e | Claude | Use brand palette colors for the FORGE Citadel offering card | Use brand palette colors for the FORGE Citadel offering card | components/home/OfferingsGrid.tsx | Committed
#89 | 2026-09-16 17:51:41 +0000 | Continuous Updates | Update | bd80955 | Claude | Merge remote-tracking branch 'origin/main' into claude/affectionate-turing-knks9g | Merge remote-tracking branch 'origin/main' into claude/affectionate-turing-knks9g | Repository root | Committed
#90 | 2026-09-16 23:22:13 +0530 | Continuous Updates | Update | 19bb787 | tanishqsharma24 | Merge pull request #3 from YashSri/claude/affectionate-turing-knks9g | Merge pull request #3 from YashSri/claude/affectionate-turing-knks9g | , components/home/OfferingsGrid.tsx | Committed
#91 | 2026-09-17 03:23:29 +0000 | Continuous Updates | Update | e8e72e7 | Claude | Make Philosophy section's scroll animation smoother and faster | Make Philosophy section's scroll animation smoother and faster | components/Philosophy.tsx | Committed
#92 | 2026-09-17 08:53:40 +0530 | Continuous Updates | Update | 8533458 | tanishqsharma24 | Merge pull request #4 from YashSri/claude/affectionate-turing-knks9g | Merge pull request #4 from YashSri/claude/affectionate-turing-knks9g | , components/Philosophy.tsx | Committed
#93 | 2026-09-17 03:26:05 +0000 | Continuous Updates | Update | 9dbb8e4 | Claude | Revert Philosophy scroll animation tuning | Revert Philosophy scroll animation tuning | components/Philosophy.tsx | Committed
#94 | 2026-09-17 08:56:14 +0530 | Continuous Updates | Update | fef8fc6 | tanishqsharma24 | Merge pull request #5 from YashSri/claude/affectionate-turing-knks9g | Merge pull request #5 from YashSri/claude/affectionate-turing-knks9g | , components/Philosophy.tsx | Committed
#95 | 2026-09-17 10:20:51 +0530 | Continuous Updates | Update | ea582ba | Winnovation | Restore all changes | Restore all changes | Repository root | Committed
#96 | 2026-09-23 16:49:02 +0530 | Continuous Updates | Update | 505f983 | Winnovation | docs: update CHANGES_LOG.txt and changes.txt with GitHub push and Vercel production deployment records | docs: update CHANGES_LOG.txt and changes.txt with GitHub push and Vercel production deployment records | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#97 | 2026-09-23 16:56:05 +0530 | Continuous Updates | Update | 5c4e9e4 | Winnovation | feat(automation): add auto_update_changelogs.py and configure recurring 2-hour cron synchronization for Excel and txt records | feat(automation): add auto_update_changelogs.py and configure recurring 2-hour cron synchronization for Excel and txt records | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt, scripts/auto_update_changelogs.py | Committed
#98 | 2026-09-24 10:44:18 +0530 | Continuous Updates | Update | f7edfe4 | Winnovation | chore(sync): automated changelog synchronization (iteration 1) | chore(sync): automated changelog synchronization (iteration 1) | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#99 | 2026-09-24 11:22:18 +0530 | Continuous Updates | Update | 7747db3 | Winnovation | feat(collaborate): redesign collaborate hero with swiss editorial layout, ambient motion, and line-based reveals | feat(collaborate): redesign collaborate hero with swiss editorial layout, ambient motion, and line-based reveals | app/collaborate/page.tsx, app/globals.css, components/collaborate/CollaborateHero.tsx | Committed
#100 | 2026-09-24 11:24:24 +0530 | Continuous Updates | Update | 0675cc2 | Winnovation | docs(changelog): record collaborate hero redesign in logs and excel report | docs(changelog): record collaborate hero redesign in logs and excel report | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#101 | 2026-09-24 12:07:17 +0530 | Continuous Updates | Update | 5473ee5 | Winnovation | feat(collaborate): redesign collaboration pathways section with asymmetric editorial grid, real photography and secondary pathway row | feat(collaborate): redesign collaboration pathways section with asymmetric editorial grid, real photography and secondary pathway row | app/collaborate/page.tsx, components/collaborate/CollaborationPathways.tsx, public/collaborate/pathway-community.jpg, public/collaborate/pathway-founder.jpg, public/collaborate/pathway-industry.jpg (+3 more) | Committed
#102 | 2026-09-24 12:11:51 +0530 | Continuous Updates | Update | b6c6820 | Winnovation | docs(changelog): update local logs and excel report for collaboration pathways redesign | docs(changelog): update local logs and excel report for collaboration pathways redesign | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#103 | 2026-09-24 12:30:44 +0530 | Continuous Updates | Update | 8d5b58c | Winnovation | feat(partner): redesign partner with forge section with segmented toggle, asymmetric card grid, and editorial photography | feat(partner): redesign partner with forge section with segmented toggle, asymmetric card grid, and editorial photography | app/collaborate/page.tsx, components/partner/PartnerAudienceSection.tsx, components/partner/PartnerWithForge.tsx, public/partner/ind-card-01.jpg, public/partner/ind-card-02.jpg (+10 more) | Committed
#104 | 2026-09-24 12:34:08 +0530 | Continuous Updates | Update | 809f7bd | Winnovation | docs(changelog): record partner with forge redesign in local changelogs and excel report | docs(changelog): record partner with forge redesign in local changelogs and excel report | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#105 | 2026-09-24 13:05:36 +0530 | Continuous Updates | Update | 42e0c05 | Winnovation | feat(collaborate): redesign Possible Collaboration Formats section with Apple-inspired Uiverse slide-up panels | feat(collaborate): redesign Possible Collaboration Formats section with Apple-inspired Uiverse slide-up panels | app/collaborate/page.tsx, components/collaborate/CollaborationFormats.tsx, public/formats/format-01.jpg, public/formats/format-02.jpg, public/formats/format-03.jpg (+6 more) | Committed
#106 | 2026-09-24 13:06:13 +0530 | Continuous Updates | Update | 839aadc | Winnovation | docs: sync changelogs and Excel report with Collaboration Formats redesign | docs: sync changelogs and Excel report with Collaboration Formats redesign | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#107 | 2026-09-24 13:26:54 +0530 | Continuous Updates | Update | b73ac8f | Winnovation | feat(collaborate): redesign Collaboration Readiness Checklist with 4x2 editorial grid and alternating slide-in panels | feat(collaborate): redesign Collaboration Readiness Checklist with 4x2 editorial grid and alternating slide-in panels | components/collaborate/ReadinessChecklist.tsx, public/checklist/checklist-01.jpg, public/checklist/checklist-02.jpg, public/checklist/checklist-03.jpg, public/checklist/checklist-04.jpg (+4 more) | Committed
#108 | 2026-09-24 13:27:30 +0530 | Continuous Updates | Update | 02c9638 | Winnovation | docs: sync changelogs and Excel report with Readiness Checklist redesign | docs: sync changelogs and Excel report with Readiness Checklist redesign | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#109 | 2026-09-24 13:39:44 +0530 | Continuous Updates | Update | 04b2ec1 | Winnovation | refactor(collaborate): remove redundant Have an Idea for Collaboration section | refactor(collaborate): remove redundant Have an Idea for Collaboration section | app/collaborate/page.tsx | Committed
#110 | 2026-09-24 13:40:41 +0530 | Continuous Updates | Update | fddcdc4 | Winnovation | docs: sync changelogs and Excel report after removing bottom collaborate CTA section | docs: sync changelogs and Excel report after removing bottom collaborate CTA section | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#111 | 2026-09-24 13:57:43 +0530 | Continuous Updates | Update | 28a9857 | Winnovation | feat(collaborate): redesign Get In Touch section with two-column editorial layout and subtle glass enquiry form | feat(collaborate): redesign Get In Touch section with two-column editorial layout and subtle glass enquiry form | app/collaborate/page.tsx, components/collaborate/CollaborateForm.tsx, public/collaborate/get-in-touch-campus.jpg | Committed
#112 | 2026-09-24 13:58:23 +0530 | Continuous Updates | Update | 00443c8 | Winnovation | docs: sync changelogs and Excel report with Get In Touch section redesign | docs: sync changelogs and Excel report with Get In Touch section redesign | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#113 | 2026-09-24 14:00:50 +0530 | Continuous Updates | Update | c2bd11e | Winnovation | docs: sync automated changelog and executive Excel report | docs: sync automated changelog and executive Excel report | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#114 | 2026-09-24 14:18:09 +0530 | Continuous Updates | Update | daa4392 | Winnovation | feat(navbar): implement premium glass navigation with sliding active pill and inner highlights | feat(navbar): implement premium glass navigation with sliding active pill and inner highlights | components/Navbar.tsx | Committed
#115 | 2026-09-24 14:19:03 +0530 | Continuous Updates | Update | 19e5470 | Winnovation | docs: sync changelogs and Excel report after navbar glass upgrade | docs: sync changelogs and Excel report after navbar glass upgrade | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#116 | 2026-09-24 14:32:02 +0530 | Continuous Updates | Update | b62fd0b | Winnovation | feat(navbar,form): integrate CodeFronts liquid glass floating capsule and scroll collapse physics | feat(navbar,form): integrate CodeFronts liquid glass floating capsule and scroll collapse physics | components/Navbar.tsx, components/collaborate/CollaborateForm.tsx | Committed
#117 | 2026-09-24 14:34:03 +0530 | Continuous Updates | Update | cd508fe | Winnovation | docs: sync changelogs and Excel report with liquid glass navbar and form updates | docs: sync changelogs and Excel report with liquid glass navbar and form updates | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#118 | 2026-09-24 14:49:13 +0530 | Continuous Updates | Update | 5719363 | Winnovation | feat(navbar,form): implement FORGE liquid glass system for navbar and community form | feat(navbar,form): implement FORGE liquid glass system for navbar and community form | app/globals.css, components/Navbar.tsx, components/collaborate/CollaborateForm.tsx | Committed
#119 | 2026-09-24 14:49:55 +0530 | Continuous Updates | Update | 77da489 | Winnovation | docs: sync changelogs and Excel report with FORGE liquid glass system | docs: sync changelogs and Excel report with FORGE liquid glass system | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#120 | 2026-09-24 14:57:42 +0530 | Continuous Updates | Update | b2d59d0 | Winnovation | fix(navbar): lock active pill alignment on scroll with stable link geometry and ResizeObserver | fix(navbar): lock active pill alignment on scroll with stable link geometry and ResizeObserver | components/Navbar.tsx | Committed
#121 | 2026-09-24 14:58:04 +0530 | Continuous Updates | Update | 2c8b82b | Winnovation | docs: sync changelogs and Excel report with navbar active pill fix | docs: sync changelogs and Excel report with navbar active pill fix | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#122 | 2026-09-24 15:19:02 +0530 | Continuous Updates | Update | f226702 | Winnovation | fix(form): center icons and normalize text alignment in collaborate form | fix(form): center icons and normalize text alignment in collaborate form | components/collaborate/CollaborateForm.tsx | Committed
#123 | 2026-09-24 15:21:16 +0530 | Continuous Updates | Update | 1de7993 | Winnovation | docs: update changelog and excel change report | docs: update changelog and excel change report | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#124 | 2026-09-24 15:45:12 +0530 | Continuous Updates | Update | b117bfe | Winnovation | feat(collaborate): redesign partner & contributor representation section with single row and editorial layout | feat(collaborate): redesign partner & contributor representation section with single row and editorial layout | components/collaborate/PartnerRepresentation.tsx, public/logos/airtel-transparent.png, public/logos/dabur-transparent.png, public/logos/infynix-transparent.png, public/logos/lightstorm-transparent.png (+3 more) | Committed
#125 | 2026-09-24 15:47:03 +0530 | Continuous Updates | Update | 8ca6958 | Winnovation | docs: update changelog and excel report for partner section redesign | docs: update changelog and excel report for partner section redesign | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#126 | 2026-09-24 15:50:26 +0530 | Continuous Updates | Update | 63ff627 | Winnovation | docs: finalize changelogs and Excel report for deployment | docs: finalize changelogs and Excel report for deployment | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#127 | 2026-09-24 16:03:05 +0530 | Continuous Updates | Update | cda7c59 | Winnovation | docs: automated changelog and Excel report sync (iteration 5) | docs: automated changelog and Excel report sync (iteration 5) | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#128 | 2026-10-02 19:51:19 +0530 | Continuous Updates | Update | 628e0b3 | Winnovation | docs: sync automated changelog and Excel report | docs: sync automated changelog and Excel report | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#129 | 2026-10-02 20:47:48 +0530 | Continuous Updates | Update | c035825 | Winnovation | feat(hero): upgrade supporter and founder logos to high-res transparent assets without background boxes | feat(hero): upgrade supporter and founder logos to high-res transparent assets without background boxes | components/Hero.tsx, public/supporters/faceoff-clean.png, public/supporters/faceoff.png, public/supporters/founder-cube-clean.png, public/supporters/founder-cube.png (+9 more) | Committed
#130 | 2026-10-02 20:49:09 +0530 | Continuous Updates | Update | 4250f8e | Winnovation | docs: update changelog and excel report for supporter logos fix | docs: update changelog and excel report for supporter logos fix | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#131 | 2026-10-02 21:19:37 +0530 | Continuous Updates | Update | 2ba47d3 | Winnovation | feat(community): link hero CTA and whats happening cards to official Commudle community and real workshop events | feat(community): link hero CTA and whats happening cards to official Commudle community and real workshop events | components/community/CommunityHero.tsx, components/community/WhatsHappeningSection.tsx, public/commudle-events/decode-the-machine.png, public/commudle-events/forging-the-ai-era.png, .../commudle-events/foundations-to-frontiers.png | Committed
#132 | 2026-10-02 21:24:04 +0530 | Continuous Updates | Update | e0a4218 | Winnovation | docs: sync changelog and excel report for commudle community integration | docs: sync changelog and excel report for commudle community integration | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#133 | 2026-10-02 21:49:41 +0530 | Continuous Updates | Update | 664c990 | Winnovation | feat(events): add automated Commudle event synchronization framework with ISR caching and live updates | feat(events): add automated Commudle event synchronization framework with ISR caching and live updates | app/api/events/route.ts, components/community/CommunityHero.tsx, components/community/WhatsHappeningSection.tsx, lib/commudle.ts, next.config.ts | Committed
#134 | 2026-10-02 21:50:29 +0530 | Continuous Updates | Update | 29c04ba | Winnovation | docs: sync changelog and excel report for automated event framework | docs: sync changelog and excel report for automated event framework | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#135 | 2026-10-02 21:54:12 +0530 | Continuous Updates | Update | e1b4da6 | Winnovation | fix(commudle): enforce Asia/Kolkata IST timezone for event start and end time formatting | fix(commudle): enforce Asia/Kolkata IST timezone for event start and end time formatting | lib/commudle.ts | Committed
#136 | 2026-10-02 21:55:19 +0530 | Continuous Updates | Update | 9300c5b | Winnovation | docs: sync changelog and excel report for IST timezone fix | docs: sync changelog and excel report for IST timezone fix | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#137 | 2026-10-02 22:00:57 +0530 | Continuous Updates | Update | c8b8fb6 | Winnovation | docs: automated changelog and Excel report sync (iteration 26) | docs: automated changelog and Excel report sync (iteration 26) | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt | Committed
#138 | 2026-10-02 22:27:30 +0530 | Continuous Updates | Update | 4a41d4d | Winnovation | fix(community): resolve event filtering for upcoming/past/all by latest date, add EventThumbnail direct unoptimized loading with fallback, and fix card opacity-0 re-render visibility | fix(community): resolve event filtering for upcoming/past/all by latest date, add EventThumbnail direct unoptimized loading with fallback, and fix card opacity-0 re-render visibility | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt, components/community/WhatsHappeningSection.tsx | Committed
#139 | 2026-10-02 23:17:54 +0530 | Continuous Updates | Update | 2cefdc4 | Winnovation | feat(navbar): update navbar logo to official FORGE brand gear logo extracted from source document | feat(navbar): update navbar logo to official FORGE brand gear logo extracted from source document | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt, components/Navbar.tsx (+6 more) | Committed
#140 | 2026-10-21 12:03:05 +0530 | Continuous Updates | Update | 4f82bbc | Winnovation | feat: incorporate 22 partner companies across collaborate and ecosystem pages | feat: incorporate 22 partner companies across collaborate and ecosystem pages | CHANGES_LOG.txt, FORGE_Website_Project_Change_Report.csv, FORGE_Website_Project_Change_Report.xlsx, changes.txt, components/collaborate/PartnerRepresentation.tsx (+24 more) | Committed

## Pages & Routes
Route | Page Title / Purpose | Core Sections Included | Interactive Features | SEO / Metadata | Build Status
/ | Homepage | Hero, Animated Stats, Philosophy Card Stack, Offerings, Voices, Footer | 60fps scroll-scrubbing card stack, numeric count-up stats, video background | Canonical + OG tags, description | 200 OK (Static SSG)
/community | Community Hub | Hero, What's Happening Events, Gallery, Stories, Participation Loop, Engagement, Advantage, The Forge Code, FAQ | Hero image corner expansion on scroll, category filters, interactive loop cards, 5-question FAQ | Canonical + OG tags, description | 200 OK (Static SSG)
/ecosystem | About & Ecosystem | Who We Are, How Innovation Scales, The Ecosystem Engine, Partner Logos, Voices | Square card geometry with blue tonal palette, philosophy-style layouts | Canonical + OG tags, description | 200 OK (Static SSG)
/programs | Programs & Certification | Program Categories, Learning Formats, Institutional Programs, Syllabus Download Modal, FAQ | Format selector, gated-download lead modal with API sync, track filtering | Canonical + OG tags, description | 200 OK (Static SSG)
/programs/[slug] | Certification Detail Tracks | Track Overview, Curriculum Modules, Outcomes, Prerequisites, Apply CTA, FAQ | Dynamic routing (5 tracks: AI, Data Science, Data Analytics, Business Analyst, etc.) | Dynamic per-track canonical metadata | 200 OK (Static SSG)
/citadel1 | The FORGE Citadel | Citadel Hero, Structural Response, Spaces Showcase, Citadel Experience Bento | Scroll-driven card stack, Uiverse hover-reveal spaces showcase, asymmetric bento | Canonical + OG tags, description | 200 OK (Static SSG)
/collaborate | Collaborate With FORGE | Partnership Tiers, Corporate Engagement Tracks, Multi-path Inquiry Modal, FAQ | Interactive tab switcher, lead capture form connected to Resend API | Canonical + OG tags, description | 200 OK (Static SSG)
/mentors | Mentors & Experts | Mentor Directory, Domain Filters, Profile Bios, Become a Mentor Modal, FAQ | Search & category filtering, modal application form | Canonical + OG tags, description | 200 OK (Static SSG)

## Assets & Media
Asset Name | File Path | Target Section | Resolution | Aspect Ratio | Design Treatment | Quality Status
faq_campus_stairs | public/faq/faq_campus_stairs.jpg | FAQ Section (All 7 Routes) | 1200 x 896 | 4:3 | Architectural photograph of campus staircase atrium with cobalt blue accent wall | Native High-Res (Replaces blurry crop)
in_person_auditorium | public/community/engagement/in_person_auditorium.png | Engagement: In-Person | 1024 x 1024 | 1:1 | Modern university auditorium session with students and daylight | Native High-Res (Replaces 196px crop)
online_laptop | public/community/engagement/online_laptop.png | Engagement: Online | 1024 x 1024 | 1:1 | Dark workstation MacBook Pro developer session with blue backlight glow | Native High-Res (Replaces 204px crop)
hybrid_split | public/community/engagement/hybrid_split.png | Engagement: Hybrid | 1376 x 768 | 16:9 | Modern meeting room with video collaboration display and students | Native High-Res (Replaces sliced mockup)
participate_photo | public/community/loop/participate_photo.jpg | Participation Loop: Step 01 | 1024 x 1024 | 1:1 | Young tech builders assembling hardware prototypes at oak workbench | Native High-Res (Replaces 290px crop)
good_people_ideas | public/community/loop/good_people_ideas.jpg | Participation Loop: Row 2 Card | 896 x 1200 | 3:4 | Sunlit architectural gallery corridor with student and blue beam | Native High-Res (Replaces 296px crop)
share_room | public/community/loop/share_room.jpg | Participation Loop: Step 06 | 1200 x 896 | 4:3 | Acoustic timber demo room with founder presenting product progress | Native High-Res (Replaces 380px crop)
learn_create_build_belong | public/community/advantage/learn_create_build_belong.png | Advantage: Learning & Development | 1200 x 896 | 4:3 | Open minimalist black notebook with architectural drawings and pen | Native High-Res (Replaces blurry mockup)
good_ideas_better_people | public/community/advantage/good_ideas_better_people.png | Advantage: Practical Experience | 1200 x 896 | 4:3 | Student engineers collaborating on robotic prototypes in research lab | Native High-Res (Replaces sliced photo)
same_people_stairs | public/community/advantage/same_people_stairs.png | Advantage: Career & Industry | 1200 x 896 | 4:3 | Two students walking across glass skyway bridge with blue steel frames | Native High-Res (Replaces stairs crop)
campus_building_banner | public/community/guidelines/campus_building_banner.png | Guidelines: Banner Card | 1376 x 768 | 16:9 | Modern building glass facade aligned right, matching left navy badge overlay | Native High-Res (Clean architecture)
forge_pillar_atrium | public/community/guidelines/forge_pillar_atrium.png | Guidelines: Row 1 Pillar Card | 1200 x 896 | 4:3 | Double-height atrium with prominent cobalt blue architectural pillar | Native High-Res (Replaces 366px crop)
students_workshop_coding | public/community/guidelines/students_workshop_coding.png | Guidelines: Row 2 Workshop Card | 896 x 1200 | 3:4 | Vertical over-the-shoulder coding session with colorful code on screen | Native High-Res (Replaces 144px crop)